## Trainee Management Module
FAMS Project Schedule
Trainee Management Module
| Project Start Date | 2020-03-17 |  |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | ThanhDT19 | [7 empty] | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04
 | time axis 2020-03-16 to 2020-05-10
WBS | TASK | ASSIGN TO | ACTUAL | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2020-03-16 to 2020-05-10
1 | [Login-Logout-Filter/Interceptor] (UC1: Log in, UC 2: Logout) |  |  |  |  | - |  |  | -
1.1 | Study requirement Q&A list | ThanhDT19 |  |  | 2020-03-17 | 2020-03-17 | 0.25 | 0% | 1
1.2 | Design Screen | ThanhDT19 |  |  | 2020-03-18 | 2020-03-18 | 0.5 | 0% | 1
1.3 | Code | ThanhDT19 |  |  | 2020-03-19 | 2020-03-19 12:00 | 1.5 | 0% | 1
1.4 | Code review & Fixbug | ThanhDT19 |  |  | 2020-03-26 | 2020-03-26 | 1 | 0% | 1
1.5 | UT Case Document | ThanhDT19 |  |  | 2020-03-30 | 2020-03-30 | 0.5 | 0% | 1
1.6 | Prepare UT scripts | ThanhDT19 |  |  | 2020-03-31 | 2020-03-31 | 0.5 | 0% | 1
1.7 | Perform UT & Fix bugs | ThanhDT19 |  |  | 2020-04-01 | 2020-04-01 | 0.5 | 0% | 1
MD | [6 empty] | 4.75
2 | [Landing Page - TBU] |  |  |  |  | - |  |  | -
2.1 | Study requirement Q&A list | ThanhDT19 |  |  | 2020-03-17 | 2020-03-17 | 0.5 | 0% | 1
2.2 | Design Screen | ThanhDT19 |  |  | 2020-03-19 | 2020-03-19 | 1 | 0% | 1
2.3 | Code | ThanhDT19 |  |  | 2020-03-19 | 2020-03-19 12:00 | 1.5 | 0% | 1
2.4 | Code review & Fixbug | ThanhDT19 |  |  | 2020-03-26 | 2020-03-26 | 1 | 0% | 1
2.5 | UT Case Document | ThanhDT19 |  |  | 2020-03-30 | 2020-03-30 | 0.5 | 0% | 1
2.6 | Prepare UT scripts | ThanhDT19 |  |  | 2020-03-31 | 2020-03-31 | 0.5 | 0% | 1
2.7 | Perform UT & Fix bugs | ThanhDT19 |  |  | 2020-04-01 | 2020-04-01 | 0.5 | 0% | 1
MD | [6 empty] | 5.5
3 | [Trainee Listing] (U: Search Trainee, UC 32: Delete Trainee Profile) |  |  |  |  | - |  |  | -
3.1 | Study requirement Q&A list | LinhNT70 |  |  | 2020-03-17 | 2020-03-17 | 0.5 | 0% | 1
3.2 | Design Screen | LinhNT70 |  |  | 2020-03-18 | 2020-03-18 | 0.5 | 0% | 1
3.3 | Code | LinhNT70 |  |  | 2020-03-19 | 2020-03-19 12:00 | 1.5 | 0% | 1
3.4 | Code review & Fixbug | LinhNT70 |  |  | 2020-03-26 | 2020-03-26 | 0.5 | 0% | 1
3.5 | UT Case Document | LinhNT70 |  |  | 2020-03-30 | 2020-03-30 | 1 | 0% | 1
3.6 | Prepare UT scripts | LinhNT70 |  |  | 2020-03-31 | 2020-03-31 | 0.5 | 0% | 1
3.7 | Perform UT & Fix bugs | LinhNT70 |  |  | 2020-04-01 | 2020-04-01 | 0.5 | 0% | 1
MD | [6 empty] | 5
4 | [Trainee Profile – Update Trainee Information] (UC 30: Update Trainee Profile) |  |  |  |  | - |  |  | -
4.1 | Study requirement Q&A list | LinhNT70 |  |  | 2020-03-17 | 2020-03-17 | 0.5 | 0% | 1
4.2 | Design Screen | LinhNT70 |  |  | 2020-03-18 | 2020-03-18 | 0.5 | 0% | 1
4.3 | Code | LinhNT70 |  |  | 2020-03-19 | 2020-03-20 | 2 | 0% | 2
4.4 | Code review & Fixbug | LinhNT70 |  |  | 2020-03-26 | 2020-03-26 | 0.5 | 0% | 1
4.5 | UT Case Document | LinhNT70 |  |  | 2020-03-30 | 2020-03-30 | 0.5 | 0% | 1
4.6 | Prepare UT scripts | LinhNT70 |  |  | 2020-03-31 | 2020-03-31 | 0.5 | 0% | 1
4.7 | Perform UT & Fix bugs | LinhNT70 |  |  | 2020-04-01 | 2020-04-01 | 0.5 | 0% | 1
MD | [6 empty] | 5
5 | [Trainee Profile – View Trainee Information] (UC 31: View Trainee Profile) |  |  |  |  | - |  |  | -
5.1 | Study requirement Q&A list | TuanPM22 |  |  | 2020-03-17 | 2020-03-16 06:00 | 0.25 | 0% | -2
5.2 | Design Screen | TuanPM22 |  |  | 2020-03-18 | 2020-03-18 | 0.5 | 0% | 1
5.3 | Code | TuanPM22 |  |  | 2020-03-19 | 2020-03-18 18:00 | 0.75 | 0% | -2
5.4 | Code review & Fixbug | TuanPM22 |  |  | 2020-03-26 | 2020-03-26 | 0.5 | 0% | 1
5.5 | UT Case Document | TuanPM22 |  |  | 2020-03-30 | 2020-03-30 | 0.5 | 0% | 1
5.6 | Prepare UT scripts | TuanPM22 |  |  | 2020-03-31 | 2020-03-30 06:00 | 0.25 | 0% | -2
5.7 | Perform UT & Fix bugs | TuanPM22 |  |  | 2020-04-01 | 2020-03-31 06:00 | 0.25 | 0% | -2
MD | [6 empty] | 3
6 | [Trainee Profile – View Training Result] --> Class1 (UC 33: Calculate Disciplinary Point -> UC35) |  |  |  |  | - |  |  | -
6.1 | Study requirement Q&A list | DuongHM |  |  | 2020-03-17 | 2020-03-17 | 1 | 0% | 1
6.2 | Design Screen | DuongHM |  |  | 2020-03-18 | 2020-03-19 | 2 | 0% | 2
6.3 | Code | DuongHM |  |  | 2020-03-19 | 2020-03-22 | 4 | 0% | 2
6.4 | Code review & Fixbug | DuongHM |  |  | 2020-03-26 | 2020-03-26 | 1 | 0% | 1
6.5 | UT Case Document | DuongHM |  |  | 2020-03-30 | 2020-03-30 | 1 | 0% | 1
6.6 | Prepare UT scripts | DuongHM |  |  | 2020-03-31 | 2020-03-31 | 1 | 0% | 1
6.7 | Perform UT & Fix bugs | DuongHM |  |  | 2020-04-01 | 2020-04-01 | 1 | 0% | 1
MD | [6 empty] | 11
7 | [Trainee Profile – View Training Result] --> Class1 (N/A) |  |  |  |  | - |  |  | -
7.1 | Study requirement Q&A list | TuanPM22 |  |  | 2020-03-17 | 2020-03-17 | 0.5 | 0% | 1
7.2 | Design Screen | TuanPM22 |  |  | 2020-03-18 | 2020-03-18 | 1 | 0% | 1
7.3 | Code | TuanPM22 |  |  | 2020-03-19 | 2020-03-21 | 3 | 0% | 2
7.4 | Code review & Fixbug | TuanPM22 |  |  | 2020-03-26 | 2020-03-26 | 1 | 0% | 1
7.5 | UT Case Document | TuanPM22 |  |  | 2020-03-30 | 2020-03-30 | 1 | 0% | 1
7.6 | Prepare UT scripts | TuanPM22 |  |  | 2020-03-31 | 2020-03-31 | 0.5 | 0% | 1
7.7 | Perform UT & Fix bugs | TuanPM22 |  |  | 2020-04-01 | 2020-04-01 | 0.5 | 0% | 1
7.5
9 | Database Design | Team Lead |  |  |  | - |  |  | -
9.1 | Database Design | ThanhDT19 |  |  | 2020-03-18 | 2020-03-18 | 1 | 0% | 1
10 | Build Project | Team Lead |  |  |  | - |  |  | -
10.1 | Build Project | ThanhDT19 |  |  | 2020-03-19 | 2020-03-19 | 0.5 | 0% | 1
11 | Message list |  |  |  |  | - |  |  | -
| Message list | LinhNT70 |  |  | 2020-03-19 | 2020-03-19 | 1 | 0% | 1
12 | Checkstyle |  |  |  |  | - |  |  | -
| Automate Code review with Checkstyle | Member |  |  | 2020-03-19 | 2020-03-19 | 0.5 | 0% | 1
13 | Exception Handler |  |  |  |  | - |  |  | -
| Exception Handler | TuanPM22 |  |  | 2020-03-19 | 2020-03-19 | 0.5 | 0% | 1
| Total (Man-days) | [5 empty] | 45.25
[5 empty] | Members | 4 | 11.3125 | (days)
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.